## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Backlog 1
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Royce Ang Jia Jie | Manav Arora | Jovan Huang Tian Chun | Clarence Hong Shi Man | Zhu Weiji | Tan Hui Zhan
Team member's mood during the this week's meeting: |  |  | Happy | Excited | Neutral | Neutral | Happy | Neutral
1 | Decide on Features of Web App | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 10 | 9.6667 | 2.1667 | 1.5 | Royce Ang Jia Jie | Everyone | Through Discussion | Yes | 1 | Neutral | 9.6667
| Estimated Task Priority（0-10） |  | 10 | 9 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 2 | 3 | 3 | 2 | 1 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 9 | 10 | 10
2 | Finish Project Proposal | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 8 | 9 | 10 | 9.8333 | 5.8333 | 7.3333 | Tan Hui Zhan | Everyone | Through Discussion | Yes | 7 | Excited | 9.3333
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 6 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 6 | 6 | 7 | 8
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 9 | 10 | 10
3 | Find Use Cases (Diagrams and Explanation) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 8 | 9 | 10 | 10 | 9.3333 | 5 | 8 | Jovan Huang Tian Chun | Everyone | Through Discussion | Yes | 7 | Neutral | 9.5
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 8 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 2 | 4 | 6 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 8 | 9 | 9
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 10 | 8 | 9
4 | Upload deliverables to Wiki | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 6.3333 | 3.3333 | 1.1667 | Manav Arora | Zhu Weiji | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 4 | 7 | 8 | 6 | 8 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 3 | 3 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 9 | 10 | 9
5 | Write Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.3333 | 0.83333 | 1 | Clarence Hong Shi Man | Jovan Huang Tian Chun | Through Discussion | Yes | 1 | Neutral | 10
| Estimated Task Priority（0-10） |  | 2 | 3 | 5 | 3 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 1 | 0 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10

## Backlog 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Royce Ang Jia Jie | Manav Arora | Jovan Huang Tian Chun | Clarence Hong Shi Man | Zhu Weiji | Tan Hui Zhan
Team member's mood during the this week's meeting: |  |  | Happy | Happy | Neutral | Neutral | Happy | Excited
1 | Update documentation (remove 'Firebase') | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 10 | 10 | 10 | 1.8333 | 1.3333 | 1 | Jovan Huang Tian Chun | Everyone | Through Discussion | Yes | 1 | Neutral | 9.3333
| Estimated Task Priority（0-10） |  | 3 | 2 | 2 | 2 | 1 | 1
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 10 | 10
2 | Come up with algorithm that recommends new friends | Task Quality Evaluation (After Task Completed) | 9 | 9 | 9 | 10 | 9 | 10 | 7.8333 | 4.6667 | 5.3333 | Zhu Weiji | - | Through Discussion | Yes | 3 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 7 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 3 | 5 | 5 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 7 | 6 | 5 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 4 | 6 | 5 | 8 | 9 | 8
3 | Setting up Github repository | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 4.3333 | 1 | 1 | Royce Ang Jia Jie | - | Through Discussion | Yes | 1 | Neutral | 10
| Estimated Task Priority（0-10） |  | 4 | 6 | 4 | 5 | 4 | 3
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 9 | 8
4 | Designing Lo-fi Prototype for Front-end | Task Quality Evaluation (After Task Completed) | 10 | 8 | 8 | 9 | 9 | 10 | 8.3333 | 6.5 | 4.5 | Royce Ang Jia Jie | - | Through Discussion | Yes | 3 | Neutral | 9
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 | 8 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 7 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 5 | 4 | 6
| Team Member's Confidence about the Task (0-10) |  | 10 | 7 | 6 | 5 | 4 | 5
5 | Defining how Front-End calls Back End API | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 9 | 8 | 8 | 7.3333 | 7.6667 | 7.8333 | Zhu Weiji | Royce Ang Jia Jie | Through Discussion | Yes | 5 | Happy | 9
| Estimated Task Priority（0-10） |  | 8 | 7 | 8 | 6 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 7 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 9 | 8 | 7 | 8 | 8 | 7
Team Member's Confidence about the Task (0-10)
6 | Refining use cases model | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 8 | 7 | 8 | 2.8333 | 1 | 1 | Clarence Hong Shi Man | - | Through Discussion | Yes | 1 | Neutral | 8.3333
| Estimated Task Priority（0-10） |  | 2 | 3 | 2 | 4 | 5 | 1
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 8 | 9 | 8 | 8
7 | Comlpete System Requirement Specification | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 10 | 8 | 9 | 9.5 | 6.3333 | 9.1667 | Manav Arora | Everyone | Through Discussion | Yes | 8 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 10 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 5 | 7 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 11 | 10 | 7 | 8 | 9 | 10
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 8 | 9 | 10
8 | Complete Quality Plan | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 8 | 9 | 9.5 | 4.3333 | 6.3333 | Clarence Hong Shi Man | Everyone | Through Discussion | Yes | 5 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 9 | 10 | 9 | 10 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 5 | 3 | 4 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 7 | 8 | 7 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 8 | 10 | 8 | 7
9 | Redux integration | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 9 | 10 | 9 | 7.1667 | 7.8333 | 6.5 | Tan Hui Zhan | Royce Ang Jia Jie | Through Discussion | Yes | 5 | Neutral | 9.5
| Estimated Task Priority（0-10） |  | 7 | 8 | 6 | 7 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 8 | 9 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 7 | 7 | 6 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 10 |  | 7 | 6 | 6 | 10
10 | Upload Documentations to Wiki | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 9 | 10 | 9 | 4.8333 | 1 | 1 | Manav Arora | - | Through Discussion | Yes | 1 | Neutral | 9.3333
| Estimated Task Priority（0-10） |  | 5 | 4 | 3 | 6 | 7 | 4
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
11 | Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 10 | 9 | 3.1667 | 1 | 1 | Clarence Hong Shi Man | - | Through Discussion | Yes | 1 | Neutral | 9.6667
| Estimated Task Priority（0-10） |  | 1 | 2 | 4 | 5 | 3 | 4
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 8 | 7 | 8

## Backlog 3
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Royce Ang Jia Jie | Manav Arora | Jovan Huang Tian Chun | Clarence Hong Shi Man | Zhu Weiji | Tan Hui Zhan
Team member's mood during the this week's meeting: |  |  | Happy | Excited | Happy | Happy | Excited | Happy
1 | Complete Project Plan | Task Quality Evaluation (After Task Completed) | 8 | 10 | 10 | 10 | 10 | 9 | 9.3333 | 3 | 11 | Jovan Huang Tian Chun | Everyone | Through Discussion | Yes | 10 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 9 | 9 | 10 | 8 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 4 | 3 | 5 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 10 | 13 | 12 | 13 | 10
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 10 | 8 | 9 | 10
2 | Complete Risk Management Plan | Task Quality Evaluation (After Task Completed) | 7 | 10 | 9 | 8 | 8 | 10 | 8.1667 | 2.8333 | 2.3333 | Manav Arora | Everyone | Through Discussion | Yes | 2 | Excited | 8.6667
| Estimated Task Priority（0-10） |  | 7 | 8 | 8 | 9 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 2 | 4 | 3 | 2 | 3 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 2 | 3 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 9 | 8 | 7
3 | Upload information to Wiki | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 1.3333 | 1 | Manav Arora | - | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 2 | 3 | 1 | 3 | 2 | 1
| Estimated Task Difficulty（0-10） |  | 1 | 2 | 1 | 1 | 2 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 1 | 1 | Clarence Hong Shi Man | - | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 3 | 2 | 2 | 3 | 1 | 1
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
5 | Refine UI UX on Front End | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 10 | 6.6667 | 6.1667 | 2.5 | Royce Ang Jia Jie | Tan Hui Zhan | Through Discussion | Yes | 2 | Happy | 9.3333
| Estimated Task Priority（0-10） |  | 7 | 7 | 6 | 7 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 6 | 6 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 4 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 5 | 7 | 6
6 | Fix API Calls bug | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 10 | 8.3333 | 6.3333 | 2.3333 | Zhu Weiji | - | Through Discussion | Yes | 2 | Excited | 9.3333
| Estimated Task Priority（0-10） |  | 9 | 10 | 7 | 6 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 6 | 6 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 2 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 7 | 5 | 10 | 6

## Backlog 4
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Royce Ang Jia Jie | Manav Arora | Jovan Huang Tian Chun | Clarence Hong Shi Man | Zhu Weiji | Tan Hui Zhan
Team member's mood during the this week's meeting: |  |  | Happy | Excited | Happy | Neutral | Excited | Happy
1 | Complete Design Report on Software Maintainability | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 9 | 8.5 | 3 | 8.1667 | Jovan Huang Tian Chun | Everyone | Through Discussion | Yes | 7 | Excited | 9.5
| Estimated Task Priority（0-10） |  | 8 | 9 | 8 | 9 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 4 | 3 | 2 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 8 | 7 | 8 | 9 | 10
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 8 | 9
2 | Complete Configuration Management Plan | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 9 | 10 | 9 | 3.1667 | 5.6667 | Tan Hui Zhan | Everyone | Through Discussion | Yes | 4 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 9 | 8 | 10 | 9 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 4 | 3 | 4 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 5 | 6 | 6 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 9 | 10
3 | Complete Release plan | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 10 | 9.5 | 4.6667 | 6.8333 | Clarence Hong Shi Man | Everyone | Through Discussion | Yes | 5 | Neutral | 9.6667
| Estimated Task Priority（0-10） |  | 9 | 10 | 9 | 10 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 4 | 6 | 4 | 6 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 8 | 10 | 7 | 6 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 9 | 10
4 | Create Presentation Slides & Rehearse for Demo | Task Quality Evaluation (After Task Completed) | 9 | 9 | 10 | 10 | 10 | 10 | 9.1667 | 6.1667 | 7.6667 | Zhu Weiji | Everyone | Through Discussion | Yes | 6 | Excited | 9.6667
| Estimated Task Priority（0-10） |  | 9 | 10 | 7 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 7 | 5 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 8 | 7 | 8 | 9 | 7
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 10 | 10 | 9 | 10
5 | Complete Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 3.1667 | 1.5 | 1.1667 | Clarence Hong Shi Man | - | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 4 | 3 | 4 | 3 | 2 | 3
| Estimated Task Difficulty（0-10） |  | 1 | 2 | 2 | 1 | 2 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
6 | Upload of Information to Wiki | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 9 | 10 | 3 | 4.1667 | 1.1667 | Manav Arora | - | Through Discussion | Yes | 1 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 3 | 4 | 2 | 3 | 4 | 2
| Estimated Task Difficulty（0-10） |  | 2 | 6 | 5 | 5 | 6 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 10 | 10 | 10
7 | Complete Change management plan | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 9 | 10 | 9 | 6 | 8.3333 | Manav Arora | - | Through Discussion | Yes | 7 | Neutral | 9.5
| Estimated Task Priority（0-10） |  | 8 | 9 | 10 | 8 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 6 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 8 | 9 | 10 | 7 | 6 | 10
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 8 | 7 | 10
8 | Create demo video | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.3333 | 5 | 2.8333 | Royce Ang Jia Jie | Jovan Huang Tian Chun | Through Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 7 | 6 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 4 | 5 | 6 | 4 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 4 | 2 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 9 | 10

## Backlog 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Royce Ang Jia Jie | Manav Arora | Jovan Huang Tian Chun | Clarence Hong Shi Man | Zhu Weiji | Tan Hui Zhan
Team member's mood during the this week's meeting: |  |  | Neutral | Neutral | Neutral | Neutral | Neutral | Neutral
1 | Test Cases and Requirements Test Coverage Report | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 10 | 9 | 8.8333 | 5.1667 | 12.1667 | Zhu Weiji | Everyone | Through Discussion | Yes | 12 | Excited | 9.6667
| Estimated Task Priority（0-10） |  | 9 | 8 | 9 | 8 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 6 | 5 | 4 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 13 | 14 | 13 | 12 | 10 | 11
| Team Member's Confidence about the Task (0-10) |  | 9 | 7 | 10 | 9 | 10 | 7
2 | Test Plan | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 10 | 9 | 8 | 9 | 7.8333 | 11.8333 | Royce Ang Jia Jie | Everyone | Through Discussion | Yes | 11 | Happy | 9
| Estimated Task Priority（0-10） |  | 9 | 8 | 10 | 9 | 8 | 10
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 7 | 8 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 13 | 14 | 12 | 11 | 10 | 11
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 8 | 7 | 8
3 | Upload documentation to Wiki | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 1.6667 | 1 | 1 | Manav Arora | Everyone | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 1 | 2 | 1 | 2 | 3 | 1
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
4 | Meeting Minutes | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 3.3333 | 1 | 1 | Jovan Huang Tian Chun | - | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 3 | 4 | 3 | 5 | 3 | 2
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10